## Budget Comparison
Num | Client | Project Manager | Total Calculated Cost | Budgeted Amount | Status
2219 | 0403 DEPCOM:2219NB -Develop PSLF & PSCAD Models for PV project in El Paso Electric footprint | Sagar Savalia | 100 | 7200 | Within Budget
2225 | 0403 DEPCOM:2225 NB - RFP - PR117 Salinas - Interconnection Compliance Study & Testing Plan | Sagar Savalia | 13931.25 | 10000 | Exceeded
2187 | 1402 North Light Energy:2187NB- Gravel Pit–03-Develop the Generic PSSEPPC &benchmark PSCAD SOLV PPCmodel | Sagar Savalia | 7212.5 | 8500 | Within Budget
2188 | 1402 North Light Energy:2188NB- PSSE&PSCAD Model development- GravelPit- 03- MOD-25/26/27 ISONEFootprint | Praveen Kumar | 23537.5 | 20000 | Exceeded
2194 | 1402 North Light Energy:2194 NB - Squirrel Run Solar - Update Interconnection package for Solar projects | Sagar Savalia | 4412.5 | 7400 | Within Budget
2197 | 1402 North Light Energy:2197 - Technical Support for 100 MW Derry Solar project in ISO-NE footprint | Praveen Kumar | 27900 | 24000 | Exceeded
2198 | 1402 North Light Energy:2198 NB - Dairy Farm Solar - Update Interconnection package | Vinoth Krishnan | 12012.5 | 7400 | Exceeded
2199 | 1402 North Light Energy:2199 NB - Goldenrod Solar - Update Interconnection package | Sagar Savalia | 5100 | 7400 | Within Budget
2200 | OCI Company Ltd:1915NB PSCAD model development/Validation for OCI Inverter XP550, BP1000, BP2200, 1402 North Light Energy:2200 NB - Goldenrod Solar II - Update Interconnection package | Vinoth Krishnan | 25468.75 | 7400 | Exceeded
2201 | 1402 North Light Energy:2201 NB - Heritage Solar - Update Interconnection package | Dr. Suresh Singh | 7254.1667 | 7400 | Within Budget
2203 | 1501 OCI Solar Power LLC.:2203B- Ausenco PPC PSCAD Model Development, Tuning, and Quality Testing– Alamo 1 | Sagar Savalia | 6400 | 10000 | Within Budget
2204 | 1501 OCI Solar Power LLC.:2204 B - OCI Alamo 1 MOD-025/26/27 Testing | Jigar | 10332.5 | 5000 | Exceeded
2175 | 1801 Ranger:2175 NB - 200 MW - PSCAD model for PV plant in SPP footprint | Dr Suresh Singh | 3387.5 | 3500 | Within Budget
2176 | 1801 Ranger:2176 NB - 75 MW - PSCAD model for BESS plant in SPP footprint | Dr. Suresh Singh | 10700 | 3500 | Exceeded
2202 | 1801 Ranger:2202 NB - Locomotive -Update Interconnection package- BESS project-PJM TC2 cycle | Jigar | 4550 | 11700 | Within Budget
2168 | 1908 Stellavise Solar Engineering:2168 NB - PSSE model for PV plant of 77MW solar project in Oklahoma | Jigar | 6850 | 4000 | Exceeded
2180 | 5 Rivers Energy Corp:2180NB - Injection Study for Meadowbrook BESS (formerly Benton Harbour BESS) | Vinoth Krishnan | 13187.5 | 8000 | Exceeded
2191 | Adani Green Energy Ltd:2191NB-300 MW Grid modelling&System Study for Wind plant in PSCAD & PSS/E-Mundra | Vinoth Krishnan | 16562.5 | 27557.54 | Within Budget
2192 | Adani Green Energy Ltd:2192NB - 239.2 MW Grid modelling & System Study for Wind plant -Navinal | Sagar Savalia | 18908.3333 | 27557.54 | Within Budget
2193 | Adani Green Energy Ltd:2193NB - 1184 MW Grid modelling & System Study for Solar plant -Siyamber | Dr. Suresh Singh | 13825 | 32676.92 | Within Budget
2189 | Apex Clean Energy Holdings:2189 NB - Downeast Wind (QP760) project in the ISONE footprint | Dr. Suresh Singh | 6850 | 30000 | Within Budget
2235 | N/A |  | 0 | 8000 | Within Budget
2234 | CEP Solar LLC:2234 NB - Dynamic model package for BESS project in PJM RRI TC2 cluster | Sagar Savalia | 4412.5 | 7800 | Within Budget
2218 | Clariant Power Systems Ltd:2218 NB - STATCOM PSCAD & PSSE model development and benchmarking | Sagar Savalia | 2375 | 12036 | Within Budget
2183 | Clean Shift Energy LLC:2183 B Keeneland Solar-Temple Hill interconnection-Review facilities study | Dr Suresh | 4325 | 5000 | Within Budget
2230 | Costen Solar Inc:2230B Queue point support-Briel Farm Solar, Gardy´s Mill and Springfield Solar |  | 1725 | 4000 | Within Budget
2208 | DESRI Development, LLC:2208 NB - DBR Texas - Interconnection application support in the SPP footprint | Sagar Savalia | 4575 | 9500 | Within Budget
2209 | DESRI Development, LLC:2209 NB - DBR New Mexico - Interconnection application support in SPP footprint | Sagar Savalia | 8887.5 | 9500 | Within Budget
2210 | DESRI Development, LLC:2210 NB - ISS New Mexico - Interconnection application support in SPP footprint | Sagar Savalia | 5600 | 9500 | Within Budget
2211 | DESRI Development, LLC:2211 NB - Noble- Interconnection application support in the SPP footprint | Vinoth Krishnan | 5925 | 9500 | Within Budget
2212 | DESRI Development, LLC:2212 NB - Jeffrey - Interconnection application support in the SPP footprint | Vinoth Krishnan | 6925 | 9500 | Within Budget
2216 | DESRI Development, LLC:2216NB - Horn shadow Solar (I) 100MW - Interconnection support | Praveen Kumar | 9300 | 4200 | Exceeded
2217 | DESRI Development, LLC:2217 NB - Horn Shadow (2) - 200 MW - Interconnection support |  | 6700 | 4200 | Exceeded
2232 | DESRI Development, LLC:2232 NB - Highland-Generic PSSE equivalent model development for BESS in PJM | Praveen Kumar | 7275 | 8900 | Within Budget
2231 | DistEnergy:2231NB Change in ksubstation design for Q1213 | Vinoth Krishnan | 1525 | 2000 | Within Budget
2172 | Emeren US, LLC:2172 NB - Orosi, Penn Valley, Bald Rock Energy (CO) - Inverter Based Resource | Dr. Suresh Singh | 125 | 2500 | Within Budget
2181 | Energix EPC US LLC:2181 NB - Interconnection support for Gladys Solar project in the PJM footprint. | Dr. Suresh Singh | 5112.5 | 11000 | Within Budget
2220 | Energix EPC US LLC:2220 NB - Waverly East - 85.43MW- Update plant level PSSE model | Vinoth Krishnan | 8125 | 7800 | Exceeded
2221 | Energix EPC US LLC:2221 NB - Waverly West - 63.82MW - Update plant level PSSE model | Vinoth Krishnan | 7150 | 7800 | Within Budget
2213 | energyRe Services, LLC:2213NB - Barn Perch-Dynamic model package for a Solar project in PJM footprint | Jigar Kumar | 7775 | 7800 | Within Budget
2222 | Enerzinx LLC:2222B - IEEE2800 Guidelines Compliance by utilities | Dr. Amritpal Singh, Amir | 7925 | 0 | Exceeded
2223 | Enerzinx LLC:2223 B - SSAT Tool Research |  | 9700 | 0 | Exceeded
2178 | N/A | Praveen Kumar | 0 | 7500 | Within Budget
2196 | Go Green USA America Corp:2196NB - PSSE Model Development & PREPA MTR compliance validation 80MW Naguabo | Vinoth Krishnan | 26250 | 50800 | Within Budget
2170 | GSMT-Enerzinx Australia JV Pty Ltd:2170 B -Malakoff Downs WF Indicative Preliminary Substation site layouts in AEMO | Vinoth Krishnan | 11482.5 | 16368 | Within Budget
2228 | GSMT-Enerzinx Australia JV Pty Ltd:2228 B - Vertiv UPS PSCAD Model RFI | Dr. Amritpal Singh | 1225 | 0 | Exceeded
2236 | GSMT-Enerzinx Australia JV Pty Ltd:2236 NB - PXiSE PSSE UDM Model Update |  | 750 | 3185.73 | Within Budget
2185 | N/A | Dr. Suresh Singh | 0 | 42000 | Within Budget
2206 | JSW Energy Limited:2206NB- 540MW Wind Project, Tuticorin-Review of reactive power capability study | Dr. Suresh Singh | 4950 | 2059.77 | Exceeded
2184 | Larsen & Toubro Ltd:2184 B - General technical support - Controller PSS®E UDM Model for Plant | Praveen Kumar | 7075 | 6000 | Exceeded
2182 | MN8 Energy:2182B Drybridge project- PSSE and PSCAD modeling support | Jigar | 18756.25 | 6400 | Exceeded
2215 | MN8 Energy:2215B - Dry Bridge Solar-Develop the as built PSCAD model & Run and tune model | Jigar Kumar | 56.25 | 20000 | Within Budget
2233 | MN8 Energy:2233 B - Mustang PV project PSCAD model | Praveen Kumar | 7062.5 | 27000 | Within Budget
2226 | N/A | Vinoth Krishnan | 0 | 10000 | Within Budget
2179 | Pure Power Engineering Inc.:2179 NB - DTE Interconnection Application Package for 10MW plant | Praveen Kumar | 2600 | 2000 | Exceeded
2171 | Q Cells USA Corporation:2171NB - Bay City Energy Park-Update Single line diagram, Site Layout, Plant lev | Dr. Suresh Singh | 2700 | 6000 | Within Budget
2186 | Q Cells USA Corporation:2186 NB - MISO MTEP24 Mapping for MISO-Central, East and West | Vinoth Krishnan | 21625 | 38000 | Within Budget
2190 | Q Cells USA Corporation:2190 NB - Bracero Pecan Storage-update the PSSE Dynamics & verify NOGRR-245 | Vinoth Krishnan | 9787.5 | 8500 | Exceeded
2224 | N/A | Sagar Savalia | 0 | 80004 | Within Budget
2227 | SunRaycer LLC:2227 B - Marcelina Storage - Generator Interconnection Application Package | Dr. Suresh Singh | 706.25 | 35200 | Within Budget
2229 | SunRaycer LLC:2229 B - Eagles Springs - Generator Interconnection Application Package | Sagar Savalia | 362.5 | 40100 | Within Budget
2195 | Tata Power:2195 NB - Restudy - TP Saurya SECI 300 MW Project - Koppal | Praveen Kumar | 50450 | 14953.87 | Exceeded
2214 | Tata Power:2214 NB - 200 MW Karuru Wind Project restudy | Dr. Suresh Singh | 36950 | 14142.34 | Exceeded
2173 | Telyon Construction LLC:2173NB Amazon-BOS27- Develop a plant-specific PSCAD model&perform Verification | Dr. Suresh Singh | 13450 | 9500 | Exceeded
2174 | Telyon Construction LLC:2174NB - Amazon- ORH3-Develop a plant-specific PSCAD model&perform Verification | Sagar Savalia | 3462.5 | 9500 | Within Budget
2207 | Tetra Tech Inc.:2207NB-Blairs Valley Project - As-Built PSSE Modelling support in PJM Footprint | Vinoth Krishnan | 8912.5 | 5000 | Exceeded
2205 | Triple Oak Power:2205NB - 200MW - Daily Mill Interconnection application support for wind project | Vinoth Krishnan | 13125 | 7800 | Exceeded